## Executive Summary
Poker Tracker — Product Report
Report date: 2026-01-26
Product overview
Poker Tracker is a lightweight web app for tracking poker session buy-ins, chip value, and profit per player. It supports multiple days/sessions, quick edits, and a statistics view that aggregates results across sessions.
Tech stack
Frontend | React 19 + TypeScript + Vite
UI interaction | @dnd-kit drag-and-drop (sortable lists)
Storage | Browser localStorage (key: poker-dashboard-v1)
Key metrics (fill in)
| Active users (DAU) | Sessions created (30d) | Retention (7d)
| 0 | 0 | 0%
| Avg session players | Crash-free sessions | NPS
| 0 | 100% | 0

## Feature Inventory
Area | Feature | Status | Notes / Acceptance Criteria
Sessions | Create new day/session | Implemented | Auto-suggest next Day N label; unique id generation.
Sessions | Switch between sessions | Implemented | Tabs show available sessions.
Players | Add player (name, paid, chip value) | Implemented | Numeric parsing and defaults.
Board | Drag-and-drop reorder players | Implemented | Uses @dnd-kit sortable; vertical list strategy.
Stats | Aggregate totals (buy-ins, chip value, profit) | Implemented | Computed across all sessions.
Storage | Persist to localStorage | Implemented | Key: poker-dashboard-v1.
UX | Profit display per player | Implemented | Profit = chipValue - paid.
Export | Export to CSV / Excel | Planned | Would enable sharing and archival.

## Risks & Issues
ID | Type | Severity | Description | Mitigation / Next step | Owner | Due
R-001 | Risk | Medium | Data loss if localStorage is cleared or browser changes. | Add export/import + optional cloud sync. | TBD
R-002 | Risk | Low | No validation for negative/invalid values beyond parsing. | Add input constraints + inline errors. | TBD
I-001 | Issue | Low | Only one column (Settled) appears after normalization. | Confirm intended workflow: add Playing/Bank columns? | TBD

## Release Plan
Milestone | Target date | Scope | Exit criteria
v0.1 |  | Stabilize core flows; add tests/lint; improve session workflow | No critical bugs; consistent calculations; basic smoke tests.
v0.2 |  | Export/Import (CSV/XLSX) + shareable report view | Export matches UI totals; import round-trip verified.
v1.0 |  | Polish UI; optional auth + cloud sync | Data durable; responsive; release notes.

## Technical Notes
Repository snapshot
Key files
File | Purpose
index.html | Vite entry HTML; contains #app mount point.
src/main.tsx | React entry; renders <App /> into #app; imports CSS.
src/App.tsx | Main UI; session/player forms; localStorage state; session normalization.
src/components/Board.tsx | DnD board rendering; drag/drop reorder + move between columns.
src/components/PlayerCard.tsx | Editable player card; shows profit; updates paid/chipValue.
src/components/StatsBoard.tsx | Aggregated stats across sessions; highlights + totals.
src/hooks/useLocalStorage.ts | Generic localStorage hook; JSON serialize/deserialize.
src/types/poker.ts | Domain types + profit helper.